## Project Tracker
Project Tracker
| Percent Over/Under to Flag: | 25%
Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2016-07-27 | 2016-09-25 | 210 | 58 | 2016-07-27 | 2016-09-30 | 1 | 300 | 0 | 63
Project 2 | Category 2 | Employee 4 | 2016-08-20 | 2016-09-20 | 400 | 30 | 2016-08-20 | 2016-09-23 | 0 | 390 | 0 | 33
Project 3 | Category 1 | Employee 2 | 2016-06-22 | 2016-08-21 | 500 | 59 | 2016-06-22 | 2016-09-03 | 0 | 500 | 0 | 71
Project 4 | Category 2 | Employee 3 | 2016-07-02 | 2016-07-12 | 250 | 10 | 2016-07-02 | 2016-07-21 | 0 | 276 | 1 | 19
Project 5 | Category 3 | Employee 2 | 2016-07-02 | 2016-08-11 | 300 | 39 | 2016-07-02 | 2016-08-17 | 0 | 310 | 0 | 45
Project 6 | Category 4 | Employee 4 | 2016-08-01 | 2016-08-11 | 500 | 10 | 2016-08-01 | 2016-08-16 | 0 | 510 | 1 | 15
Project 7 | Category 5 | Employee 1 | 2016-08-17 | 2016-09-10 | 750 | 23 | 2016-08-17 | 2016-09-15 | 0 | 790 | 0 | 28
Project 8 | Category 2 | Employee 1 | 2016-08-22 | 2016-09-30 | 450 | 38 | 2016-08-16 | 2016-09-25 | 0 | 430 | 0 | 39
project 9 | Category 4 | Employee 1 | 2016-02-05 | 2016-06-09 | 250 | 124 | 2016-03-05 | 2016-05-05 | 0 | 200 | 1 | 60
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS